## Fixes
ID | Module / View | Problem Description | Reported Behavior | Status | Reported Dated | Resolved Date | Comments
1 | Coach | Shop Request Missing Data | The "Select Balgruha" dropdown menu is empty, preventing coaches from requesting items. | Fixed |  |  | Changed user?._id to user?.id in RequestItemModal.jsx to match AuthContext
2 | Coach | Empty Course Folders | The Courses section appears incomplete as no content is visible in the folders. | Fixed
3 | Purchase Manager | Missing Supplier Data | Vendors added via Admin view are not appearing in the Purchase Supplier list.
4 | Admin | Missing Approval Action | No "Approve" button is visible for purchase requests sent from the Purchase Manager. | Fixed |  |  | Added Purchase Management permission to admin role; Fixed approval workflow
5 | Admin | Permission Error | Admin credentials receive an "Access Denied" error when trying to create/add courses. | Fixed
6 | Backend / purchase-requests.js | Express route ordering causing 400 errors | /pending-count endpoint returning 400 because matched as :id parameter | Fixed | 2026-02-24 | 2026-02-24 | Moved static routes before dynamic /:id route
7 | Backend / shop.js | Product filtering not showing products when purchaseCategory doesn't match | Products not appearing in dropdown when category selected | Fixed | 2026-02-24 | 2026-02-24 | Added fallback to check category field
8 | Backend / api.js | Out of stock products hidden from purchase request | PM seeing fewer products than admin (15 vs 24) | Fixed | 2026-02-24 | 2026-02-24 | Added inStock=false parameter to API calls
9 | Frontend / ProductManagement.jsx | Category filter mismatch with product creation | Category filter options different from product creation categories | Fixed | 2026-02-24 | 2026-02-24 | Updated filter to match: ISF Shop, Medicines, Consumables, Repairs, Infra, Others
10 | Frontend / CreatePurchaseRequestModal.jsx | Missing estimated unit cost input field | Cannot enter costs when creating purchase request | Fixed | 2026-02-24 | 2026-02-24 | Added estimated unit cost input with grand total calculation
11 | Frontend / ShopInventoryView.jsx | PM not seeing pending_approval requests | Large purchase requests not visible to PM after creation | Fixed | 2026-02-24 | 2026-02-24 | Changed default status filter to 'active', added Pending Approval tab
12 | Backend / purchaseRequestController.js | Approval workflow skipping fulfillment steps | After approval, PM sees "Update Stock" instead of normal workflow | Fixed | 2026-02-24 | 2026-02-24 | Changed approval status from 'approved' to 'pending'
13 | Frontend / CreatePurchaseRequestModal.jsx | Edit modal not pre-filling existing data | Products, deadline, and other fields empty when editing | In Progress | 2026-02-24 | 2026-02-24 | Added key prop to force remount, added estimated costs to edit data